## RTM
Req ID | Module # | Module | Title | Priority | Functional Requirement | Sub-reqs | Interfaces | Prototype status | Gap / notes | Shared services | Release | Planned sprints | Size | Story points | Decision refs | Test cases | SME / UAT owner | Delivery status
REG-REQ01 | 1 | User Registration & Account Management | Tax Club Member Registration | High | The system shall allow an eligible user to register for a TRA Tax Club account through the Mobile Application or Web Application by providing the mandatory personal, contact, membership and institutional information. | 9 | Mobile / Web / Admin | Partial | API register exists (name, email, phone, password, user_type, institution). Missing: DOB/age band, gender, region, consent/guardian, registration reference, Pending Verification status (currently auto-verified + token issued), inactive-institution check, member-facing registration UI in repo. UPDATE 16-Oct-2026: Web + API registration with Pending Verification and reference number (branch feat/laravel13-livewire-tailwind). Still missing: DOB/age band, guardian consent capture, region, confirmation notification. | Workflow, Audience, Notifications, Cases/Numbering, Safeguarding, Scoped RBAC | R1 | S2–S6 | L | 6 | D-04, D-06, D-07 | TC-REG-REQ01-01..09 | TRA Taxpayer Education / Tax Club Programme Responsible Officer | Done
REG-REQ02 | 1 | User Registration & Account Management | Tax Club Membership Verification | High | The system shall allow an authorized user to verify, approve or reject a submitted Tax Club membership registration. | 9 | Mobile / Web / Admin | Not started | No implementation in prototype. UPDATE 16-Oct-2026: Verification queue with filters, approve/reject with reason, officer and time recorded. Still missing: coordinator/patron scope, applicant notification. UPDATE 17-Oct-2026: Verification queue now scoped: patrons see and decide only their own institution; TRA officers need view_all_registrations. Still missing: region-scoped coordinators, applicant notification. | Workflow, Notifications, Audit, Cases/Numbering, Scoped RBAC | R1 | S2–S6 | M | 5 | D-05, D-09 | TC-REG-REQ02-01..09 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Done
REG-REQ03 | 1 | User Registration & Account Management | Account Activation | High | The system shall activate a Tax Club member account after successful membership verification and allow the verified member to access services permitted for their assigned membership category. | 8 | Mobile / Web | Not started | No implementation in prototype. UPDATE 16-Oct-2026: Approval activates the account and issues an interim membership number. Still missing: notification, final number format (D-03). | Workflow, Audience, Notifications, Audit, Cases/Numbering | R1 | S2–S6 | M | 5 |  | TC-REG-REQ03-01..08 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Done
REG-REQ04 | 1 | User Registration & Account Management | User Login | High | The system shall allow a registered and active user to securely log in to the TRA Tax Club Digital Platform through the Mobile Application or Web Application using approved authentication credentials. | 9 | Mobile / Web | Partial | Email+password login with Sanctum token and permission list; single-session. Missing: phone login, lockout/rate limit, login audit, token expiry, suspended-status enforcement, MFA for staff. UPDATE 16-Oct-2026: Web sign-in by phone or email with rate limiting and status checks; API login blocks non-active accounts. Still missing: login audit, token expiry, staff MFA. | Workflow, Audit | R1 | S2–S6 | L | 6 | D-07, D-08 | TC-REG-REQ04-01..09 | TRA ICT Security / Tax Club Programme Responsible Officer | In progress
REG-REQ05 | 1 | User Registration & Account Management | Account Recovery and Credential Reset | High | The system shall allow a registered user who cannot access their account to securely recover the account or reset their authentication credentials through an approved identity-verification mechanism. | 10 | Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering | R1 | S2–S6 | L | 8 | D-07 | TC-REG-REQ05-01..10 | TRA ICT Security / System Administration Team | Done
REG-REQ06 | 1 | User Registration & Account Management | Account Suspension, Deactivation and Reactivation | High | The system shall allow an authorized user to suspend, deactivate or reactivate a Tax Club user account in accordance with approved membership, moderation, security and administrative rules. | 10 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit, Safeguarding | R1 | S2–S6 | M | 5 |  | TC-REG-REQ06-01..10 | TRA Tax Club Programme Coordinator / Moderator / ICT Security Representative | Planned
REG-REQ07 | 1 | User Registration & Account Management | Transition of Student Member to Alumni | High | The system shall allow an eligible Tax Club member to transition from active student membership to Tax Club Alumni status while retaining approved membership history, learning achievements and participation records. | 10 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit, Cases/Numbering | R1 | S2–S6 | L | 8 | D-12 | TC-REG-REQ07-01..10 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Planned
PRO-REQ01 | 2 | Member Profile & Digital Membership | View Member Profile | High | The system shall allow a registered Tax Club member to view their profile information through the Mobile Application or Web Application. | 8 | Mobile / Web | Partial | GET /auth/me returns basic profile and institution. Missing: membership status/category display rules, achievements, badges, certificates. | Workflow, Scoped RBAC | R1 | S2–S6 | S | 2 |  | TC-PRO-REQ01-01..08 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Planned
PRO-REQ02 | 2 | Member Profile & Digital Membership | Update Member Profile | High | The system shall allow a Tax Club member to update permitted personal and profile information through the Mobile Application or Web Application. | 8 | Mobile / Web | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Safeguarding | R1 | S2–S6 | M | 5 |  | TC-PRO-REQ02-01..08 | TRA Tax Club Programme Coordinator / System Administrator | Planned
PRO-REQ03 | 2 | Member Profile & Digital Membership | Member Profile Privacy Management | High | The system shall control the visibility of member profile information based on user role, membership category, privacy rules and approved safeguarding requirements. | 7 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Cases/Numbering, Safeguarding | R1 | S2–S6 | L | 8 | D-04 | TC-PRO-REQ03-01..07 | TRA ICT Security / Tax Club Programme Coordinator / Data Protection Responsible Officer | Planned
MEM-REQ01 | 2 | Member Profile & Digital Membership | Generate Digital Tax Club Membership Number | High | The system shall generate a unique Tax Club membership number for each successfully verified and activated Tax Club member. | 7 | Mobile / Web / Admin | Partial | Random TRA-XXXXXXXX assigned at registration. Must be issued only on activation, in approved format, sequence-based, retained for alumni. | Workflow, Audit | R1 | S2–S6 | S | 2 | D-03 | TC-MEM-REQ01-01..07 | TRA Tax Club Programme Coordinator / System Administrator | Done
MEM-REQ02 | 2 | Member Profile & Digital Membership | Digital Tax Club Membership Card | High | The system shall generate and display a digital Tax Club membership card for each verified and active Tax Club member through the Mobile Application and Web Application. | 9 | Mobile / Web | Not started | No implementation in prototype. | Workflow | R1 | S2–S6 | L | 8 | D-03 | TC-MEM-REQ02-01..09 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Done
MEM-REQ03 | 2 | Member Profile & Digital Membership | Digital Membership Verification | High | The system shall allow an authorized user to verify the validity and current status of a Tax Club member's digital membership using the membership number, QR code or other approved verification mechanism. | 7 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience | R1 | S2–S6 | M | 5 | D-13 | TC-MEM-REQ03-01..07 | TRA Tax Club Programme Coordinator / Tax Club Patron | Done
MEM-REQ04 | 2 | Member Profile & Digital Membership | Membership Status Management | High | The system shall maintain and display the current Tax Club membership status of each member throughout the membership lifecycle. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit | R1 | S2–S6 | M | 5 |  | TC-MEM-REQ04-01..08 | TRA Tax Club Programme Coordinator / System Administrator | In progress
INS-REQ01 | 3 | Institution & Tax Club Management | Institution Registration | High | The system shall allow an authorized user to register an educational institution participating in the TRA Tax Club programme through the Administration Portal. | 10 | Mobile / Web / Admin | Partial | Create institution with name, type, region, district. Missing: unique code, contacts, has_tax_club, status, duplicate check, created_by, region/district master data. UPDATE 17-Oct-2026: Admin form + CSV import: category, 31-region list, district, contacts, generated code (e.g. DSM-S-0042), duplicate check, created_by, active on creation. | Workflow, Audit, Cases/Numbering, Scoped RBAC | R1 | S2–S6 | M | 4 |  | TC-INS-REQ01-01..10 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Done
INS-REQ02 | 3 | Institution & Tax Club Management | Update Institution Information | High | The system shall allow an authorized user to update approved information relating to a registered educational institution. | 8 | Mobile / Web / Admin | Partial | Update endpoint exists. Missing: audit history (before/after), identifier protection. UPDATE 17-Oct-2026: Edit form with code protected and duplicate check. Still missing: before/after audit log of field changes (shared Audit service). | Workflow, Audit, Scoped RBAC | R1 | S2–S6 | S | 2 |  | TC-INS-REQ02-01..08 | TRA Tax Club Programme Coordinator / System Administrator | In progress
INS-REQ03 | 3 | Institution & Tax Club Management | Institution Activation and Deactivation | High | The system shall allow an authorized user to activate or deactivate a registered institution for participation in the TRA Tax Club Digital Platform. | 9 | Mobile / Web / Admin | Not started | No implementation in prototype. UPDATE 17-Oct-2026: Activate/deactivate with mandatory reason and status history; inactive institutions hidden from registration and the public API; members kept. | Workflow, Audit, Cases/Numbering | R1 | S2–S6 | S | 3 |  | TC-INS-REQ03-01..09 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Done
INS-REQ04 | 3 | Institution & Tax Club Management | Tax Club Establishment and Management | High | The system shall allow an authorized user to establish and manage a Tax Club under a registered educational institution. | 9 | Mobile / Web / Admin | Not started | No implementation in prototype. UPDATE 17-Oct-2026: Tax Club per institution, establishment date, status with reason, one active club per institution. | Workflow, Audience, Audit, Cases/Numbering, Scoped RBAC | R1 | S2–S6 | M | 5 |  | TC-INS-REQ04-01..09 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Done
INS-REQ05 | 3 | Institution & Tax Club Management | Tax Club Patron Assignment | High | The system shall allow an authorized user to assign, replace or remove a Tax Club Patron responsible for coordinating Tax Club activities within a registered educational institution. | 9 | Admin | Not started | No implementation in prototype. UPDATE 17-Oct-2026: Assign patron by phone (existing user or new staff account with one-time password), start date, end with reason, history kept, Patron role granted/removed. Still missing: notification to the patron (Notifications module). | Workflow, Notifications, Audit, Cases/Numbering | R1 | S2–S6 | M | 5 |  | TC-INS-REQ05-01..09 | TRA Tax Club Programme Coordinator / Participating Educational Institution Representative | In progress
INS-REQ06 | 3 | Institution & Tax Club Management | TRA Tax Club Coordinator Assignment | High | The system shall allow an authorized user to assign TRA Tax Club Coordinators to institutions, Tax Clubs, regions or other approved programme areas. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audit, Cases/Numbering, Scoped RBAC | R1 | S2–S6 | L | 8 | D-09 | TC-INS-REQ06-01..08 | TRA Taxpayer Education Management / Tax Club Programme Coordinator | Planned
INS-REQ07 | 3 | Institution & Tax Club Management | Search and View Institutions and Tax Clubs | Medium | The system shall allow authorized users to search, filter and view registered institutions and their associated Tax Clubs according to the user's access rights. | 10 | Mobile / Web / Admin | Partial | List supports search by name and filter by type/region. Missing: district/status/club filters, patron/coordinator display, stats, scope-restricted results. UPDATE 17-Oct-2026: Search by name/code/district; filters by category, region, status; shows Tax Club and patrons. Still missing: coordinator display and region-scoped results (INS-REQ06). | Workflow, Scoped RBAC | R1 | S2–S6 | M | 4 |  | TC-INS-REQ07-01..10 | TRA Tax Club Programme Coordinator / Tax Education Management | In progress
INS-REQ08 | 3 | Institution & Tax Club Management | Institution and Tax Club Membership Statistics | Medium | The system shall calculate and display approved membership statistics for each registered institution and Tax Club. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. UPDATE 17-Oct-2026: Per-institution active, waiting and alumni counts (staff excluded). Still missing: category breakdown and dashboard/report export. | Workflow, Scoped RBAC | R1 | S2–S6 | M | 5 |  | TC-INS-REQ08-01..08 | TRA Tax Club Programme Coordinator / Monitoring and Evaluation Responsible Officer | In progress
LRN-REQ01 | 4 | Learning & Content Management | Create Learning Content | High | The system shall allow an authorized content officer to create and save Tax Club learning content through the Administration Portal. | 9 | Mobile / Web / Admin | Partial | Admin create with title, type (video/article/infographic/quiz), file_url, rich-text body. Missing: categories, summary/objectives, uploads with validation, Draft status, content code, more content types. | Workflow, Audience, Audit, Cases/Numbering | R2 | S7–S9 | L | 6 |  | TC-LRN-REQ01-01..09 | TRA Taxpayer Education / Content Management Responsible Officer | Planned
LRN-REQ02 | 4 | Learning & Content Management | Review and Approve Learning Content | High | The system shall allow an authorized reviewer or approver to review, approve, reject or return submitted learning content for correction before publication. | 9 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R2 | S7–S9 | M | 5 |  | TC-LRN-REQ02-01..09 | TRA Taxpayer Education Content Reviewer / Relevant TRA Subject Matter Expert | Planned
LRN-REQ03 | 4 | Learning & Content Management | Publish, Schedule, Unpublish and Archive Learning Content | High | The system shall allow an authorized user to publish, schedule, unpublish or archive approved learning content through the Administration Portal. | 9 | Mobile / Web / Admin | Partial | is_active toggle and published_at only. Missing: approved-only publishing, scheduling, expiry, archive, history. | Workflow, Audience, Audit | R2 | S7–S9 | M | 4 |  | TC-LRN-REQ03-01..09 | TRA Taxpayer Education / Content Publication Responsible Officer | Planned
LRN-REQ04 | 4 | Learning & Content Management | Categorize and Target Learning Content | High | The system shall allow authorized users to categorize learning content and define the member groups to which the content is applicable. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Cases/Numbering, Safeguarding, Scoped RBAC | R2 | S7–S9 | M | 5 |  | TC-LRN-REQ04-01..08 | TRA Taxpayer Education / Learning Content Management Officer | Planned
LRN-REQ05 | 4 | Learning & Content Management | Access and View Learning Content | High | The system shall allow an authenticated eligible member to access and view approved published learning content through the Mobile Application and Web Application. | 8 | Mobile / Web | Partial | Members list/view active content with own progress. Missing: targeting, browse by category, engagement analytics, resume, low-bandwidth media. | Workflow, Audience, Cases/Numbering | R2 | S7–S9 | L | 6 |  | TC-LRN-REQ05-01..08 | TRA Taxpayer Education / Tax Club Programme Responsible Officer | Planned
LRN-REQ06 | 4 | Learning & Content Management | Learning Module Progress Tracking | High | The system shall record and maintain an eligible member’s progress through structured learning modules and display the member’s current learning status. | 9 | Mobile / Web / Admin | Partial | user_progress per content item (not_started/in_progress/completed). Missing: structured modules/lessons, mandatory components, resume position, version-aware history. | Workflow, Audience, Audit | R2 | S7–S9 | L | 6 |  | TC-LRN-REQ06-01..09 | TRA Taxpayer Education / Monitoring and Evaluation Responsible Officer | Planned
LRN-REQ07 | 4 | Learning & Content Management | Search and Filter Learning Content | Medium | The system shall allow members to search and filter approved learning content through the Mobile Application and Web Application. | 9 | Mobile / Web / Admin | Partial | Title search and type filter. Missing: keywords/tags, category & level filters, relevance ordering, eligibility filtering. | Workflow, Audience | R2 | S7–S9 | M | 4 |  | TC-LRN-REQ07-01..09 | TRA Taxpayer Education / Content Management Responsible Officer | Planned
LRN-REQ08 | 4 | Learning & Content Management | Content Versioning and Tax Information Updates | High | The system shall maintain controlled versions of learning content when approved information is revised and shall ensure that members are presented with the current published version. | 9 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Safeguarding | R2 | S7–S9 | L | 8 | D-10 | TC-LRN-REQ08-01..09 | TRA Taxpayer Education / Relevant Tax Subject Matter Expert | Planned
COM-REQ01 | 5 | Questions, Expert Engagement & Community | Submit Tax-Related Question | High | The system shall allow an authenticated Tax Club member to submit a tax-related question to TRA through the Mobile Application or Web Application. | 9 | Mobile / Web | Not started | No implementation in prototype. | Workflow, Notifications, Cases/Numbering | R4 | S14–S17 | M | 5 |  | TC-COM-REQ01-01..09 | TRA Taxpayer Education / Tax Subject Matter Expert | Planned
COM-REQ02 | 5 | Questions, Expert Engagement & Community | Review, Categorize and Assign Submitted Questions | High | The system shall allow an authorized TRA officer to review, categorize and assign submitted member questions to an appropriate TRA subject matter expert for response. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering, Scoped RBAC | R4 | S14–S17 | M | 5 |  | TC-COM-REQ02-01..08 | TRA Taxpayer Education Coordinator / Tax Subject Matter Expert | Planned
COM-REQ03 | 5 | Questions, Expert Engagement & Community | TRA Expert Response to Member Questions | High | The system shall allow an assigned TRA subject matter expert to prepare and submit a response to a member question through the Administration Portal. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering, Scoped RBAC | R4 | S14–S17 | M | 5 |  | TC-COM-REQ03-01..08 | TRA Tax Subject Matter Expert / Responsible Technical Department | Planned
COM-REQ04 | 5 | Questions, Expert Engagement & Community | Review, Approve and Publish Questions and Answers | High | The system shall allow an authorized reviewer to review, approve, reject or return an expert response and publish approved questions and answers to the intended member or approved knowledge area. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering, Scoped RBAC | R4 | S14–S17 | M | 5 | D-14 | TC-COM-REQ04-01..08 | TRA Taxpayer Education Content Reviewer / Tax Subject Matter Expert | Planned
COM-REQ05 | 5 | Questions, Expert Engagement & Community | Create and Manage Community Discussion Spaces | High | The system shall allow authorized users to create and manage moderated community discussion spaces for national, institutional, thematic, event, competition or other approved Tax Club engagement purposes. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Audit, Cases/Numbering, Safeguarding | R4 | S14–S17 | L | 8 |  | TC-COM-REQ05-01..08 | TRA Tax Club Programme Coordinator / Community Moderator | Planned
COM-REQ06 | 5 | Questions, Expert Engagement & Community | Create Community Posts, Comments and Replies | High | The system shall allow eligible Tax Club members to create posts, comments and replies within discussion spaces for which they have participation rights. | 8 | Mobile / Web | Partial | Global forum posts + replies; edit/soft-delete own. Missing: discussion spaces, content rules validation, mentions/notifications, participation restrictions. | Workflow, Audience, Notifications, Audit, Safeguarding | R4 | S14–S17 | L | 6 |  | TC-COM-REQ06-01..08 | TRA Community Moderator / Tax Club Programme Coordinator | Planned
COM-REQ07 | 5 | Questions, Expert Engagement & Community | Report Inappropriate Content or User Behaviour | High | The system shall allow a user to report inappropriate community content or user behaviour for review by an authorized moderator. | 8 | Admin | Not started | No implementation in prototype. Built once with SAF-REQ01 (case engine). | Workflow, Audit, Cases/Numbering, Safeguarding | R4 | S14–S17 | S | 2 |  | TC-COM-REQ07-01..08 | TRA Community Moderator / Safeguarding Responsible Officer | Planned
COM-REQ08 | 5 | Questions, Expert Engagement & Community | Moderate Community Content and User Participation | High | The system shall allow an authorized moderator to review reported or flagged community content and apply approved moderation actions to content or user participation. | 8 | Admin | Partial | Admin can soft-delete posts. Missing: moderation queue, actions (warn/hide/restrict/escalate), reasons, restore, history. Built once with SAF-REQ03. | Workflow, Notifications, Audit, Cases/Numbering, Safeguarding | R4 | S14–S17 | S | 2 |  | TC-COM-REQ08-01..08 | TRA Community Moderation Lead / ICT Security / Safeguarding Responsible Officer | Planned
COM-REQ09 | 5 | Questions, Expert Engagement & Community | Inter-Institution Collaboration Groups | Medium | The system shall allow authorized users to create controlled collaboration groups that enable approved Tax Club members from different institutions to participate in joint learning, projects, campaigns or competitions. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Cases/Numbering, Safeguarding | R4 | S14–S17 | M | 5 |  | TC-COM-REQ09-01..08 | TRA Tax Club Programme Coordinator / Community Moderator | Planned
ALM-REQ01 | 6 | Alumni & Mentorship | Alumni Profile and Membership Management | High | The system shall allow an approved Tax Club alumnus to maintain an alumni profile and access services permitted for the Alumni membership category after completion of the student-to-alumni transition process. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow | R5 | S18–S19 | M | 5 |  | TC-ALM-REQ01-01..08 | TRA Tax Club Programme Coordinator / Alumni Programme Responsible Officer | Planned
ALM-REQ02 | 6 | Alumni & Mentorship | Alumni Directory and Networking | Medium | The system shall provide an approved alumni directory and networking capability that allows eligible users to discover and connect with Tax Club alumni according to configured privacy and safeguarding rules. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Cases/Numbering, Safeguarding, Scoped RBAC | R5 | S18–S19 | L | 8 |  | TC-ALM-REQ02-01..08 | TRA Alumni Programme Responsible Officer / Data Protection or Safeguarding Representative | Planned
ALM-REQ03 | 6 | Alumni & Mentorship | Alumni Experience Sharing and Sessions | Medium | The system shall allow authorized users to organize and publish approved alumni experience-sharing content, webinars, career talks and Tax Club sessions for eligible members. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Safeguarding | R5 | S18–S19 | M | 5 |  | TC-ALM-REQ03-01..08 | TRA Tax Club Alumni Programme Coordinator / Taxpayer Education Officer | Planned
MNT-REQ01 | 6 | Alumni & Mentorship | Mentor Registration and Approval | High | The system shall allow an eligible alumnus or other approved person to apply to participate as a Tax Club mentor and shall allow an authorized TRA user to review and approve or reject the mentor application. | 9 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit, Cases/Numbering, Safeguarding | R5 | S18–S19 | M | 5 |  | TC-MNT-REQ01-01..09 | TRA Tax Club Programme Coordinator / Safeguarding Responsible Officer | Planned
MNT-REQ02 | 6 | Alumni & Mentorship | Mentorship Request by Member | High | The system shall allow an eligible Tax Club member to submit a mentorship request indicating approved mentorship interests and support needs. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Cases/Numbering, Safeguarding, Scoped RBAC | R5 | S18–S19 | M | 5 |  | TC-MNT-REQ02-01..08 | TRA Tax Club Programme Coordinator / Mentorship Programme Officer | Planned
MNT-REQ03 | 6 | Alumni & Mentorship | Mentor-Mentee Matching and Approval | High | The system shall allow an authorized coordinator to match an approved mentor with an eligible mentee and establish a mentorship relationship in accordance with approved matching and safeguarding rules. | 9 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit, Cases/Numbering, Safeguarding | R5 | S18–S19 | L | 8 | D-11 | TC-MNT-REQ03-01..09 | TRA Mentorship Programme Coordinator / Safeguarding Responsible Officer | Planned
MNT-REQ04 | 6 | Alumni & Mentorship | Mentorship Engagement and Progress Tracking | Medium | The system shall allow authorized participants and coordinators to record and monitor approved mentorship activities, milestones and status without exposing unnecessary private communication content. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Notifications, Safeguarding | R5 | S18–S19 | M | 5 |  | TC-MNT-REQ04-01..08 | TRA Mentorship Programme Coordinator / Monitoring and Evaluation Officer | Planned
MNT-REQ05 | 6 | Alumni & Mentorship | Mentorship Completion and Closure | Medium | The system shall allow an authorized participant or coordinator to complete or close a mentorship relationship and record approved outcome information. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Safeguarding | R5 | S18–S19 | S | 3 |  | TC-MNT-REQ05-01..08 | TRA Mentorship Programme Coordinator / Monitoring and Evaluation Officer | Planned
MNT-REQ06 | 6 | Alumni & Mentorship | Mentorship Safeguarding and Monitoring | High | The system shall enforce approved safeguarding, supervision, reporting and communication controls for mentorship activities, particularly where a mentee is a minor. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audit, Cases/Numbering, Safeguarding | R5 | S18–S19 | L | 8 | D-11 | TC-MNT-REQ06-01..08 | TRA Safeguarding Responsible Officer / ICT Security / Tax Club Programme Coordinator | Planned
OPP-REQ01 | 7 | Employment & Opportunities | Create Employment and Development Opportunity | High | The system shall allow an authorized user to create an employment, internship, scholarship, volunteering, training, entrepreneurship or other approved development opportunity through the Administration Portal. | 9 | Admin | Partial | Create with title, organization, type (job/internship/volunteer), description, deadline. Missing: more categories, eligibility/audience, opening date, application channel, attachments, Draft status. | Workflow, Audience, Audit | R3 | S10–S13 | M | 4 |  | TC-OPP-REQ01-01..09 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Planned
OPP-REQ02 | 7 | Employment & Opportunities | Review and Approve Opportunity | High | The system shall allow an authorized reviewer or approver to review, approve, reject or return a submitted opportunity for correction before it is made available to Tax Club members. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R3 | S10–S13 | S | 3 |  | TC-OPP-REQ02-01..08 | TRA Tax Club Programme Coordinator / Authorized Opportunity Reviewer | Planned
OPP-REQ03 | 7 | Employment & Opportunities | Publish, Schedule, Close and Archive Opportunity | High | The system shall allow an authorized user to publish an approved opportunity, schedule its publication, automatically close it at the approved deadline, and archive it after expiry or withdrawal. | 8 | Admin | Partial | is_active flag and deadline. Missing: approval gate, scheduling, auto-close, withdrawal reason, archive, history. | Workflow, Audience, Notifications, Audit | R3 | S10–S13 | M | 4 |  | TC-OPP-REQ03-01..08 | TRA Tax Club Programme Coordinator / Content Administrator | Planned
OPP-REQ04 | 7 | Employment & Opportunities | Browse, Search and View Opportunities | High | The system shall allow eligible users to browse, search, filter and view approved active opportunities through the Mobile Application and Web Application. | 9 | Mobile / Web | Partial | Members list/view active opportunities. Missing: filters, eligibility, closing-soon indicator, expired exclusion by date. | Workflow, Audience | R3 | S10–S13 | M | 4 |  | TC-OPP-REQ04-01..09 | TRA Tax Club Programme Coordinator / Career and Youth Engagement Responsible Officer | Planned
OPP-REQ05 | 7 | Employment & Opportunities | Opportunity Eligibility and Audience Targeting | High | The system shall allow an authorized user to define opportunity eligibility and target-audience rules and shall use those rules to control or prioritize opportunity visibility for relevant Tax Club users. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Safeguarding, Scoped RBAC | R3 | S10–S13 | M | 5 |  | TC-OPP-REQ05-01..08 | TRA Tax Club Programme Coordinator / Data Protection and Safeguarding Responsible Officer | Planned
OPP-REQ06 | 7 | Employment & Opportunities | Save Opportunity and Access Application Channel | Medium | The system shall allow a member to save or bookmark an active opportunity for later reference and access the approved external or internal application channel specified for that opportunity. | 9 | Mobile / Web | Not started | No implementation in prototype. | Workflow | R3 | S10–S13 | M | 5 |  | TC-OPP-REQ06-01..09 | TRA Tax Club Programme Coordinator / ICT Security Representative | Planned
OPP-REQ07 | 7 | Employment & Opportunities | Career Guidance and Employability Resources | Medium | The system shall provide members with approved career-guidance and employability resources, including CV preparation, interview preparation, career awareness and other youth-development materials, through the Mobile Application and Web Application. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience | R3 | S10–S13 | S | 3 |  | TC-OPP-REQ07-01..08 | TRA Tax Club Programme Coordinator / Career Guidance Content Responsible Officer | Planned
OPP-REQ08 | 7 | Employment & Opportunities | Opportunity Engagement Monitoring and Reporting | Medium | The system shall capture and provide authorized users with aggregated engagement information on published opportunities and career resources for programme monitoring and reporting. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Audit, Scoped RBAC | R3 | S10–S13 | M | 5 |  | TC-OPP-REQ08-01..08 | TRA Monitoring and Evaluation Responsible Officer / Tax Club Programme Coordinator | Planned
GAM-REQ01 | 8 | Quiz & Gamification | Create Quiz | High | The system shall allow an authorized user to create a tax education or approved learning quiz through the Administration Portal. | 9 | Mobile / Web / Admin | Partial | Create quiz with title, description, optional content link. Missing: category/module, target membership, instructions, pass mark (hard-coded 50%), practice vs scored, Draft workflow. | Workflow, Audience, Audit | R2 | S7–S9 | M | 4 |  | TC-GAM-REQ01-01..09 | TRA Taxpayer Education / Tax Club Learning Content Responsible Officer | Planned
GAM-REQ02 | 8 | Quiz & Gamification | Manage Quiz Questions and Answer Options | High | The system shall allow an authorized quiz creator to add, edit, remove and arrange questions and answer options within a quiz. | 9 | Admin | Partial | Questions (multiple choice, true/false), answers, points, reorder. Missing: multiple-selection type, media, explanations, validation of correct answer before submit. | Workflow, Cases/Numbering | R2 | S7–S9 | M | 4 |  | TC-GAM-REQ02-01..09 | TRA Tax Education Content Officer / Subject Matter Expert | Planned
GAM-REQ03 | 8 | Quiz & Gamification | Review and Approve Quiz | High | The system shall allow an authorized reviewer or approver to review a submitted quiz and approve, reject or return it for correction before publication. | 9 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R2 | S7–S9 | S | 3 |  | TC-GAM-REQ03-01..09 | TRA Taxpayer Education Content Reviewer / Approved Tax Subject Matter Expert | Planned
GAM-REQ04 | 8 | Quiz & Gamification | Publish and Schedule Quiz | High | The system shall allow an authorized user to publish an approved quiz immediately or schedule it for a defined availability period. | 9 | Mobile / Web / Admin | Partial | is_active toggle only. Missing: approved-only, scheduling open/close, targeting, notifications, publication history. | Workflow, Audience, Notifications, Audit, Scoped RBAC | R2 | S7–S9 | M | 4 |  | TC-GAM-REQ04-01..09 | TRA Tax Club Programme Coordinator / Tax Education Officer | Planned
GAM-REQ05 | 8 | Quiz & Gamification | Participate in Quiz | High | The system shall allow an eligible Tax Club member to access and attempt an available quiz through the Mobile Application or Web Application. | 10 | Mobile / Web | Partial | Members fetch questions (correct answers hidden) and submit. Missing: eligibility, instructions screen, time limit, attempt limit, autosave, server-side start time. | Workflow, Audience, Audit | R2 | S7–S9 | L | 6 |  | TC-GAM-REQ05-01..10 | TRA Tax Club Learning Programme Officer / Tax Club Member Representative | Planned
GAM-REQ06 | 8 | Quiz & Gamification | Automated Scoring and Quiz Results | High | The system shall automatically calculate and record a member's quiz score based on the approved answer key and scoring rules after a valid quiz attempt is submitted. | 9 | Mobile / Web / Admin | Partial | Automatic scoring, percentage, pass/fail, per-question responses. Missing: configurable pass mark, result release timing, answer/explanation visibility rules, aggregate reporting; error text leaked on failure. | Workflow, Audit | R2 | S7–S9 | M | 4 |  | TC-GAM-REQ06-01..09 | TRA Tax Education Content Officer / Assessment Responsible Officer | Planned
GAM-REQ07 | 8 | Quiz & Gamification | Manage Quiz Attempts, Time Limits and Retakes | High | The system shall enforce configured quiz attempt limits, time limits, retake rules and attempt status for each eligible member. | 9 | Mobile / Web / Admin | Partial | Unlimited retakes; best attempt retained; client-reported time_spent. Missing: max attempts, server-enforced time limit, auto-submit, configurable retained result. | Workflow, Audience, Audit | R2 | S7–S9 | M | 4 |  | TC-GAM-REQ07-01..09 | TRA Tax Club Programme Coordinator / Quiz Administrator | Planned
GAM-REQ08 | 8 | Quiz & Gamification | Points and Gamification Rules | High | The system shall calculate and award points to eligible members based on approved Tax Club learning and engagement activities according to configurable gamification rules. | 9 | Mobile / Web / Admin | Partial | Points = quiz points on best attempt, stored as totals on users. Missing: configurable rules, points ledger, duplicate prevention, admin corrections with audit. | Workflow, Audience, Audit, Cases/Numbering | R2 | S7–S9 | L | 6 | D-15 | TC-GAM-REQ08-01..09 | TRA Tax Club Programme Coordinator / Gamification Responsible Officer | Planned
GAM-REQ09 | 8 | Quiz & Gamification | Badges and Achievements | Medium | The system shall automatically award and display digital badges or achievements when a member satisfies approved achievement criteria. | 9 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R2 | S7–S9 | M | 5 |  | TC-GAM-REQ09-01..09 | TRA Tax Club Programme Coordinator / Learning and Gamification Content Officer | Planned
GAM-REQ10 | 8 | Quiz & Gamification | Leaderboard Management | Medium | The system shall calculate and display approved leaderboards based on configured gamification metrics and eligibility rules. | 10 | Mobile / Web / Admin | Partial | Global (public, unauthenticated) and per-quiz leaderboards. Missing: periods, institution/region boards, enable/disable, minor privacy (currently exposes full names + membership IDs publicly). | Workflow, Audience, Safeguarding, Scoped RBAC | R2 | S7–S9 | L | 6 | D-04 | TC-GAM-REQ10-01..10 | TRA Tax Club Programme Coordinator / Gamification Responsible Officer | In progress
CMP-REQ01 | 9 | Competition, Rewards & Certificates | Create Competition | High | The system shall allow an authorized user to create a Tax Club competition through the Administration Portal by defining its purpose, participation rules, schedule and applicable competition activities. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Audit, Scoped RBAC | R4 | S14–S17 | M | 5 |  | TC-CMP-REQ01-01..08 | TRA Tax Club Programme Coordinator / Responsible Taxpayer Education Officer | Planned
CMP-REQ02 | 9 | Competition, Rewards & Certificates | Review and Approve Competition | High | The system shall allow an authorized reviewer or approver to review, approve, reject or return a draft competition for correction before publication. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R4 | S14–S17 | S | 3 |  | TC-CMP-REQ02-01..08 | TRA Tax Club Programme Coordinator / Authorized Competition Approver | Planned
CMP-REQ03 | 9 | Competition, Rewards & Certificates | Publish Competition and Manage Registration | High | The system shall allow an approved competition to be published or scheduled for publication and shall allow eligible members to register or enroll where registration is required. | 9 | Mobile / Web | Not started | No implementation in prototype. | Workflow, Audience, Notifications | R4 | S14–S17 | M | 5 |  | TC-CMP-REQ03-01..09 | TRA Tax Club Programme Coordinator / Competition Administrator | Planned
CMP-REQ04 | 9 | Competition, Rewards & Certificates | Participate in Competition and Submit Entry | High | The system shall allow an eligible registered member to participate in a competition and submit the required competition activity or entry within the configured participation period. | 8 | Mobile / Web | Not started | No implementation in prototype. | Workflow, Audience, Audit | R4 | S14–S17 | L | 8 |  | TC-CMP-REQ04-01..08 | TRA Tax Club Programme Coordinator / Competition Administrator | Planned
CMP-REQ05 | 9 | Competition, Rewards & Certificates | Competition Scoring, Ranking and Results Approval | High | The system shall calculate or record competition scores according to approved rules, rank participants and allow authorized users to review and approve final results before publication. | 9 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Audit, Cases/Numbering | R4 | S14–S17 | L | 8 |  | TC-CMP-REQ05-01..09 | TRA Tax Club Programme Coordinator / Competition Judge or Approver | Planned
RWD-REQ01 | 9 | Competition, Rewards & Certificates | Configure Competition Rewards and Recognition | Medium | The system shall allow an authorized user to configure approved rewards and recognition associated with a competition, achievement or other eligible Tax Club activity. | 7 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Audit | R4 | S14–S17 | M | 5 | D-16 | TC-RWD-REQ01-01..07 | TRA Tax Club Programme Coordinator / Authorized Programme Approver | Planned
RWD-REQ02 | 9 | Competition, Rewards & Certificates | Award, Issue and Track Rewards | Medium | The system shall allow authorized users to assign approved rewards to eligible members and maintain a record of reward issuance, collection or delivery status. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Audit, Cases/Numbering | R4 | S14–S17 | M | 5 | D-16 | TC-RWD-REQ02-01..08 | TRA Tax Club Programme Coordinator / Reward Administration Responsible Officer | Planned
CER-REQ01 | 9 | Competition, Rewards & Certificates | Generate and Issue Digital Certificates | Medium | The system shall generate and issue digital certificates to eligible Tax Club members for approved competitions, learning achievements, events or other recognized activities. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R4 | S14–S17 | L | 8 | D-17 | TC-CER-REQ01-01..08 | TRA Tax Club Programme Coordinator / Authorized Certificate Issuer | Planned
CER-REQ02 | 9 | Competition, Rewards & Certificates | Verify Digital Certificate Authenticity | Medium | The system shall allow a user to verify the authenticity and current status of a digital Tax Club certificate using its unique identifier, QR code or other approved verification mechanism. | 6 | Admin | Not started | No implementation in prototype. | Workflow, Audit | R4 | S14–S17 | M | 5 |  | TC-CER-REQ02-01..06 | TRA Tax Club Programme Coordinator / ICT Security Representative | Planned
EVT-REQ01 | 10 | Events & Campaigns | Create Event or Campaign | High | The system shall allow an authorized user to create a Tax Club event or campaign through the Administration Portal by defining its purpose, schedule, location, target audience and participation arrangements. | 8 | Mobile / Web / Admin | Partial | Create event with title, description, location, start/end. Missing: type/mode, objective, organizer, online info, audience, capacity, registration config, materials, Draft. | Workflow, Audience, Notifications, Audit, Scoped RBAC | R3 | S10–S13 | M | 4 |  | TC-EVT-REQ01-01..08 | TRA Tax Club Programme Coordinator / Tax Education Officer | Planned
EVT-REQ02 | 10 | Events & Campaigns | Review and Approve Event or Campaign | High | The system shall allow an authorized reviewer or approver to review, approve, reject or return a proposed event or campaign for correction before publication where approval is required. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R3 | S10–S13 | S | 3 |  | TC-EVT-REQ02-01..08 | TRA Tax Club Programme Coordinator / Authorized Event Approver | Planned
EVT-REQ03 | 10 | Events & Campaigns | Publish, Schedule and Target Event or Campaign | High | The system shall allow an approved event or campaign to be published immediately or scheduled for publication to the configured eligible audience. | 7 | Mobile / Web / Admin | Partial | is_active flag only. Missing: approval gate, scheduling, targeting, auto status, postpone/cancel. | Workflow, Audience, Notifications, Audit, Scoped RBAC | R3 | S10–S13 | M | 4 |  | TC-EVT-REQ03-01..07 | TRA Tax Club Programme Coordinator / Event Organizer | Planned
EVT-REQ04 | 10 | Events & Campaigns | Event Registration and RSVP | High | The system shall allow an eligible Tax Club member to register for or confirm attendance at an event where registration or RSVP is required. | 8 | Mobile / Web / Admin | Partial | Register / cancel registration; admin attendee list. Missing: eligibility, deadline/cut-off, confirmation, registration questions. | Workflow, Audience | R3 | S10–S13 | M | 4 |  | TC-EVT-REQ04-01..08 | TRA Tax Club Programme Coordinator / Event Organizer | Planned
EVT-REQ05 | 10 | Events & Campaigns | Event Capacity and Waitlist Management | Medium | The system shall enforce configured participant capacity for an event and support a waitlist where the event reaches maximum registration capacity and waitlisting is enabled. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R3 | S10–S13 | M | 5 |  | TC-EVT-REQ05-01..08 | TRA Tax Club Programme Coordinator / Event Organizer | Planned
EVT-REQ06 | 10 | Events & Campaigns | Event Attendance and Check-In | High | The system shall allow authorized users to record and verify participant attendance at applicable Tax Club events using approved manual, QR-based or other check-in methods. | 7 | Mobile / Web / Admin | Partial | Registration status enum includes 'attended' but no check-in flow. Missing: QR/manual check-in, officer/device record, corrections with reason. | Workflow, Audience, Audit | R3 | S10–S13 | L | 6 |  | TC-EVT-REQ06-01..07 | TRA Tax Club Programme Coordinator / Event Attendance Officer | Planned
EVT-REQ07 | 10 | Events & Campaigns | Event and Campaign Updates, Materials and Participant Information | Medium | The system shall allow authorized event organizers to publish approved updates, instructions and materials related to an active or upcoming event or campaign for access by the appropriate participants. | 7 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications | R3 | S10–S13 | M | 5 |  | TC-EVT-REQ07-01..07 | TRA Tax Club Programme Coordinator / Event Organizer | Planned
EVT-REQ08 | 10 | Events & Campaigns | Close Event or Campaign and Generate Participation Summary | High | The system shall allow an authorized organizer to close a completed event or campaign and generate an operational summary of registration, attendance and participation information. | 9 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audit, Scoped RBAC | R3 | S10–S13 | M | 5 |  | TC-EVT-REQ08-01..09 | TRA Tax Club Programme Coordinator / Monitoring and Evaluation Responsible Officer | Planned
NOT-REQ01 | 11 | Notification Management | Notification Template and Channel Configuration | High | The system shall allow an authorized administrator to configure notification templates, supported delivery channels and notification categories for the TRA Tax Club Digital Platform. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit | R1 | S2–S6 | L | 8 | D-18 | TC-NOT-REQ01-01..08 | TRA Tax Club Programme Coordinator / ICT Application Administrator | Planned
NOT-REQ02 | 11 | Notification Management | Automated Transactional Notifications | High | The system shall automatically generate and send notifications to users when predefined system or business events occur. | 7 | Mobile / Web | Not started | No implementation in prototype. | Workflow, Notifications, Audit | R1 | S2–S6 | L | 8 | D-18 | TC-NOT-REQ02-01..07 | TRA Tax Club Programme Coordinator / ICT Application Administrator | In progress
NOT-REQ03 | 11 | Notification Management | Targeted and Broadcast Notifications | High | The system shall allow an authorized user to create and send targeted or broadcast notifications to selected Tax Club audiences through the Administration Portal. | 8 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit, Scoped RBAC | R3 | S10–S13 | L | 8 |  | TC-NOT-REQ03-01..08 | TRA Tax Club Programme Coordinator / Taxpayer Education Communication Officer | Planned
NOT-REQ04 | 11 | Notification Management | Scheduled Notifications and Reminders | Medium | The system shall support automated and administrator-configured reminder notifications for time-bound Tax Club activities. | 7 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R3 | S10–S13 | M | 5 |  | TC-NOT-REQ04-01..07 | TRA Tax Club Programme Coordinator / ICT Application Administrator | Planned
NOT-REQ05 | 11 | Notification Management | User Notification Preferences | Medium | The system shall allow a user to manage permitted notification preferences for optional notification categories and delivery channels through the Mobile Application or Web Application. | 7 | Mobile / Web | Not started | No implementation in prototype. | Audience, Notifications, Safeguarding | R2 | S7–S9 | M | 5 |  | TC-NOT-REQ05-01..07 | TRA Tax Club Programme Coordinator / ICT Application Administrator | Planned
NOT-REQ06 | 11 | Notification Management | Notification Inbox and Read Status | High | The system shall provide an in-app notification inbox that allows authenticated users to view and manage notifications received through the Tax Club Digital Platform. | 8 | Mobile / Web | Not started | No implementation in prototype. | Workflow, Notifications, Audit | R1 | S2–S6 | M | 5 |  | TC-NOT-REQ06-01..08 | TRA Tax Club Programme Coordinator / ICT Application Administrator | Planned
NOT-REQ07 | 11 | Notification Management | Notification Delivery Tracking, Failure and Retry | Medium | The system shall track notification delivery attempts and support controlled retry of failed notifications for applicable delivery channels. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit | R3 | S10–S13 | M | 5 |  | TC-NOT-REQ07-01..08 | TRA ICT Operations / Application Administrator | In progress
FBK-REQ01 | 12 | Feedback, User Safety & Moderation | Submit Feedback and Suggestions | High | The system shall allow an authenticated user to submit feedback, suggestions or platform-related concerns through the Mobile Application or Web Application. | 9 | Mobile / Web | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering, Safeguarding | R3 | S10–S13 | M | 5 |  | TC-FBK-REQ01-01..09 | TRA Tax Club Programme Coordinator / User Support Responsible Officer | Planned
FBK-REQ02 | 12 | Feedback, User Safety & Moderation | Feedback Classification and Assignment | Medium | The system shall allow an authorized user to classify, prioritize and assign submitted feedback to the appropriate responsible officer or functional area. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering | R3 | S10–S13 | S | 3 |  | TC-FBK-REQ02-01..08 | TRA Tax Club Programme Coordinator / ICT Support Lead | Planned
FBK-REQ03 | 12 | Feedback, User Safety & Moderation | Feedback Review, Response and Closure | High | The system shall allow an authorized officer to review submitted feedback, record a response or action taken, and close the feedback when resolution is completed. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering, Safeguarding | R3 | S10–S13 | M | 5 |  | TC-FBK-REQ03-01..08 | TRA Tax Club Programme Coordinator / Responsible Service Owner | Planned
FBK-REQ04 | 12 | Feedback, User Safety & Moderation | Feedback Status Tracking | Medium | The system shall allow a user to view the current status and permitted response information for feedback they have submitted. | 6 | Admin | Not started | No implementation in prototype. | Workflow, Cases/Numbering | R3 | S10–S13 | S | 3 |  | TC-FBK-REQ04-01..06 | TRA Tax Club Programme Coordinator / ICT Application Administrator | Planned
SAF-REQ01 | 12 | Feedback, User Safety & Moderation | Report Inappropriate Content or User Behaviour | High | The system shall allow a permitted user to report inappropriate content, unsafe behaviour or suspected violations of Tax Club community rules. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audience, Notifications, Audit, Cases/Numbering, Safeguarding | R4 | S14–S17 | M | 5 |  | TC-SAF-REQ01-01..08 | TRA Tax Club Programme Coordinator / Safeguarding or Moderation Responsible Officer | Planned
SAF-REQ02 | 12 | Feedback, User Safety & Moderation | Moderation Case Review and Investigation | High | The system shall allow an authorized moderator to review, investigate, prioritize and manage reports of inappropriate content or user behaviour. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering, Safeguarding, Scoped RBAC | R4 | S14–S17 | L | 8 |  | TC-SAF-REQ02-01..08 | TRA Moderation / Safeguarding Responsible Officer | Planned
SAF-REQ03 | 12 | Feedback, User Safety & Moderation | Content Moderation Actions | High | The system shall allow an authorized moderator to apply approved moderation actions to user-generated content that violates Tax Club community rules. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering, Safeguarding | R4 | S14–S17 | M | 5 |  | TC-SAF-REQ03-01..08 | TRA Community Moderator / Tax Club Programme Coordinator | Planned
SAF-REQ04 | 12 | Feedback, User Safety & Moderation | User Warning, Restriction, Suspension and Deactivation | High | The system shall allow an authorized moderator or administrator to apply approved account-level actions to users who violate community, safeguarding or security rules. | 9 | Mobile / Web / Admin | Not started | No implementation in prototype. | Workflow, Notifications, Audit, Cases/Numbering, Safeguarding | R4 | S14–S17 | L | 8 |  | TC-SAF-REQ04-01..09 | TRA Tax Club Programme Coordinator / Safeguarding Officer / ICT Security Representative | Planned
SAF-REQ05 | 12 | Feedback, User Safety & Moderation | Minor Safeguarding Controls and Escalation | High | The system shall enforce approved safeguarding controls for users classified as minors and support escalation of safety concerns to designated responsible officers. | 9 | Admin | Not started | No implementation in prototype. | Workflow, Audit, Cases/Numbering, Safeguarding | R4 | S14–S17 | L | 8 | D-04, D-11 | TC-SAF-REQ05-01..09 | TRA Designated Safeguarding Responsible Officer / Tax Club Programme Coordinator | Planned
SAF-REQ06 | 12 | Feedback, User Safety & Moderation | Moderation Audit Trail and Safety Reporting | High | The system shall maintain an auditable record of moderation and safeguarding activities and provide authorized users with safety and moderation reports. | 8 | Admin | Not started | No implementation in prototype. | Workflow, Audit, Cases/Numbering, Safeguarding | R4 | S14–S17 | M | 5 | D-10 | TC-SAF-REQ06-01..08 | TRA Safeguarding / Moderation Responsible Officer / ICT Security Representative | Planned

## Foundations backlog
Item | Description | Release | Size | Story points
R0-01 | Security remediation: rotate secrets, purge history, secret scanning | R0 | S | 3
R0-02 | Monorepo + Docker Compose dev environment | R0 | M | 5
R0-03 | CI/CD pipeline (lint, test, SAST, build, deploy to dev/staging) | R0 | L | 8
R0-04 | Fix migrations (uuidMorphs, sessions), SQLite/MySQL test DB, factories | R0 | M | 5
R0-05 | Feature-test harness + baseline tests for existing endpoints | R0 | M | 5
R0-06 | OpenAPI generation + typed TS API client package | R0 | M | 5
R0-07 | Audit Log service | R0 | M | 5
R0-08 | Numbering/sequence service | R0 | S | 3
R0-09 | Publishing Workflow engine + review queue API | R0 | L | 8
R0-10 | Audience Rules engine | R1 | L | 8
R0-11 | Scoped RBAC + Policies + role seeding | R0 | L | 8
R0-12 | Media service (upload, scan, signed URLs, thumbnails) | R1 | M | 5
R0-13 | Case Management engine | R1 | L | 8
R0-14 | Design system (Figma), UX for R1 journeys, usability test with students (design track — not in dev velocity) | R0 | L | 0
R0-15 | Expo member app scaffold: navigation, auth shell, i18n en/sw, offline cache | R0 | L | 8
R0-16 | Admin portal fixes: single router, permission slugs, lockfile, API client | R0 | M | 5
RH-01 | Data migration from prototype + rehearsal | RH | M | 5
RH-02 | Load & performance testing, tuning | RH | M | 5
RH-03 | Reporting module (proposed M13) dashboards & exports | R5 | XL | 13
RH-04 | Platform administration (proposed M14): master data, settings, audit viewer | R3 | L | 8

## Release plan
Release | Name | Sprints | Start | End | Scope | SRS reqs | SRS points | Foundation points | Total points | Capacity (pts) | Load %
R0 | Stabilise & Foundations | S0–S1 | 2026-11-02 | 2026-11-27 | Security remediation, monorepo, CI/CD, Docker, migrations fixed, test harness, OpenAPI, shared services (Audit, Numbering, Workflow, Scoped RBAC), design system, Expo scaffold, i18n |  |  |  |  | 70
R1 | Membership MVP (pilot) | S2–S6 | 2026-11-30 | 2027-02-26 | M1 Registration & accounts, M2 Profile & digital card, M3 Institutions & clubs, core Notifications (templates, transactional, inbox), Audience, Media and Case engines. Pilot with 10 institutions |  |  |  |  | 175
R2 | Learn & Play — national launch | S7–S9 | 2027-03-01 | 2027-04-09 | M4 Learning, M8 Quiz & gamification, notification preferences. App Store / Play Store public launch |  |  |  |  | 105
R3 | Engage | S10–S13 | 2027-04-12 | 2027-06-04 | M10 Events & campaigns, M7 Opportunities, Feedback, broadcasts, reminders, delivery tracking, platform administration (master data, settings, audit viewer) |  |  |  |  | 140
R4 | Community, Safety & Competitions | S14–S17 | 2027-06-07 | 2027-07-30 | M12 Safety & moderation engine (first), M5 Q&A & community, M9 Competitions, rewards & certificates |  |  |  |  | 140
R5 | Alumni, Mentorship & Reporting | S18–S19 | 2027-08-02 | 2027-08-27 | M6 Alumni & mentorship, reporting module (proposed M13), performance tuning |  |  |  |  | 70
RH | Hardening, Pen-test, Final UAT, Go-live | S20–S21 | 2027-08-30 | 2027-09-24 | Independent penetration test, load test, regression, final UAT sign-off, data migration rehearsal, production go-live, then 4 weeks hypercare |  |  |  |  | 70
Total
Assumption: velocity 35 pts/sprint in every sprint for the recommended team in 07-execution-plan.md §4. Points include API, admin, member app and automated tests. Re-baseline after S3 using measured velocity.

## Sprint calendar
Sprint | Start (Mon) | End (Fri) | Release | Sprint review / demo
S0 | 2026-11-02 | 2026-11-13 | R0 | Kick-off + architecture sign-off
S1 | 2026-11-16 | 2026-11-27 | R0 | Demo to TRA product owner; UAT of previous release on staging
S2 | 2026-11-30 | 2026-12-11 | R1 | Demo to TRA product owner; UAT of previous release on staging
S3 | 2027-01-04 | 2027-01-15 | R1 | Demo to TRA product owner; UAT of previous release on staging
S4 | 2027-01-18 | 2027-01-29 | R1 | Demo to TRA product owner; UAT of previous release on staging
S5 | 2027-02-01 | 2027-02-12 | R1 | Demo to TRA product owner; UAT of previous release on staging
S6 | 2027-02-15 | 2027-02-26 | R1 | Demo to TRA product owner; UAT of previous release on staging
S7 | 2027-03-01 | 2027-03-12 | R2 | Demo to TRA product owner; UAT of previous release on staging
S8 | 2027-03-15 | 2027-03-26 | R2 | Demo to TRA product owner; UAT of previous release on staging
S9 | 2027-03-29 | 2027-04-09 | R2 | Demo to TRA product owner; UAT of previous release on staging
S10 | 2027-04-12 | 2027-04-23 | R3 | Demo to TRA product owner; UAT of previous release on staging
S11 | 2027-04-26 | 2027-05-07 | R3 | Demo to TRA product owner; UAT of previous release on staging
S12 | 2027-05-10 | 2027-05-21 | R3 | Demo to TRA product owner; UAT of previous release on staging
S13 | 2027-05-24 | 2027-06-04 | R3 | Demo to TRA product owner; UAT of previous release on staging
S14 | 2027-06-07 | 2027-06-18 | R4 | Demo to TRA product owner; UAT of previous release on staging
S15 | 2027-06-21 | 2027-07-02 | R4 | Demo to TRA product owner; UAT of previous release on staging
S16 | 2027-07-05 | 2027-07-16 | R4 | Demo to TRA product owner; UAT of previous release on staging
S17 | 2027-07-19 | 2027-07-30 | R4 | Demo to TRA product owner; UAT of previous release on staging
S18 | 2027-08-02 | 2027-08-13 | R5 | Demo to TRA product owner; UAT of previous release on staging
S19 | 2027-08-16 | 2027-08-27 | R5 | Demo to TRA product owner; UAT of previous release on staging
S20 | 2027-08-30 | 2027-09-10 | RH | Demo to TRA product owner; UAT of previous release on staging
S21 | 2027-09-13 | 2027-09-24 | RH | Demo to TRA product owner; UAT of previous release on staging
Buffer week 14-18 Dec 2026 (defects, tech debt, pilot prep) and holiday freeze 21-Dec-2026 to 03-Jan-2027 (no sprint). Hypercare runs 4 weeks after S21.

## Legend
Field | Meaning
Prototype status | Partial = some behaviour exists in commit 7ad3d35 but key rules are missing; Not started = nothing usable
Size | S = 3 pts, M = 5, L = 8, XL = 13 (full stack: API + admin portal + member app + tests). Partial items discounted 25%
Shared services | Platform services from 02-solution-architecture.md §4 that the requirement depends on (auto-derived from SRS text; verify in refinement)
Decision refs | Open business decisions in 09-decisions-and-business-rules-register.md that block final acceptance criteria
Test cases | One test case per related sub-requirement, numbered TC-<ReqID>-NN; UAT scripts derived from SRS Behavior + Exceptional rows
Delivery status | Maintained by the delivery team each sprint (drop-down)